Draft 15/9/2003

European Environment Agency

2004 Annual Management Plan

# Index

# EEA Mission Statement

# Objectives of the EEA

# Indicators of EEA performance

# Work programme

1. Strategic approaches to providing an information system

2. Action on tackling climate change

3. Action on nature and biodiversity

4. Action on environment & health and quality of life

5. Action on sustainable use & management of natural resources and wastes

6. Action on international issues

7. Underpinning environmental policy making

# Administration and Corporate Affairs

# Communications highlights

###### 1. EEA Mission Statement

Our mission is to:

- provide support for sustainable development

- help achieve significant and measurable improvement in Europe's environment and

- provide timely, targeted, relevant and reliable information to policy making agents and the public

# 2. Objectives of the EEA

- to improve the EEA/EIONET information system including quality assurance procedures to support more effectively the development of EEA products and services and to ensure the full integration of new members

- to provide information, analyses and assessments in support of:

  - Kyoto protocol and future climate change policies

  - EU target to halt biodiversity loss by 2010

  - spatial issues relating to land, water and biodiversity

  - policies to improve human health and the quality of life as related to the environment

  - policies on sustainable use and management of natural resources and wastes, including the identification of best practices

- to provide advice and briefings to the Commission, Parliament and Presidencies to advance new environment policy areas (for example health) across relevant sectors especially agriculture, chemicals, energy and transport

- to work further together with international organisations, secretariats of international conventions and countries to ensure that respective activities tackling environmental issues are properly coordinated and the effectiveness of the activities enhanced

- to become known and trusted as the organisation which provides regular updates of overall progress towards meeting environment objectives in the context of sustainable development

- to this end, develop scenarios in cooperation with others as well as analyse and document emerging issues

- to communicate environmental information effectively to Europe’s citizens using the full range of communication channels

- to enhance the value of our activities, products and services for our clients in relation to the resources at our disposal.

# 3. Strategic Indicators of the EEA performance

| # Strategic indicator | Diagnostic indicator |
| --- | --- |
| # Financial perspective |  |
| Budget | Budget implementation |
|  | Budget execution |
| Sound financial management | Number of ‘severe’ audit and discharge remarks |
| # Client perspective |  |
| Relevance | Number of demands and recognitions by key stakeholders |
|  | Web site – client sessions |
|  | Publications sales |
|  | Quotation index |
| Timeliness | Time to market |
| Image | Client satisfaction index |
| # Business process |  |
| Supply chain | Time lag in data availability |
|  | Data quality |
|  | Data volume |
| Knowledge sharing | Number of MoUs |
| Data handling | Update rate of indicators |
| Publications - timeliness | Throughput time |
|  | Publications plan execution |
| Internal support - timeliness | Throughput time for tenders |
|  | Processing time commitments/payments |
|  | Internal support survey |
| # Learning and growth |  |
| Work force | Average recruitment time |
|  | Employee turn over rate |
| Capability | Training per employee |
|  | Deviation from training needs identified in career development plan |
|  | Competency gap |
| Motivation | Absence |
|  | Staff satisfaction survey |

# 4. Work programme

1. Strategic approaches to providing an information system (504w,1200kEuro)

1.1 The EEA/Eionet Information System

a) Eionet coordination

Eionet will be further developed by adjusting to the needs arising from the Corporate Strategy 2004-2008 and more closely involving the National Reference Centres. Planning will be improved with help of a new electronic application for scheduling Eionet activities and requested inputs to EEA.

b) Core set of indicators

The core set will be published. A web-based indicator management system will be built to track production of indicator factsheets. The 7th Eionet priority data flows report will assess countries’ performance on delivery and data quality. The Eionet priority data flows will be extended in line with the agreed core set.

c) Reportnet developments

A proposal will be drafted on how to re-engineer current business processes in countries to report more efficiently to the international level. Reportnet tools will increasingly be used to underpin data flows, and further improved and better integrated to enhance quality assurance, tracking and transparency.

d) Relations with EU institutions

Links with Eurostat and JRC will be strengthened on data sharing (eg spatial data sets) and development of common methodologies for indicators (eg on waste). Support will continue to DGEnv on the review of reporting initiative using indicators, priority data flows and Reportnet tools as main EEA contributions.

e) Data Service

A data policy will be adopted and implemented. All data collected for regular reporting and reference data will be processed and the service extended by including model data and outputs. Web tools to enable users to access and analyse data will be improved. Access to European Topic Centre data will be brought into a seamless system. Closely linked to the Data Service, EPER will be launched.

1.2 European environmental shared information system

a) Integrated Spatial Information System

The system will be scoped and a 5-year implementation plan agreed with data partners. Pilot activities focused on land/biodiversity/water interactions will be progressed based on Corine Land Cover 2000 updates from countries and the European System of Environmental Accounts methodology.  Support will continue to DG Environment on the INSPIRE initiative and EEA will seek partnerships and funding through GMES to support implementation of the

Integrated Spatial Information System in the medium-term.

2. Tackling climate change (72w,1100kEuro)

2.1 Distance to targets assessments

Regular indicator-based assessment of the effectiveness of national and EU policies in achieving the Kyoto- and burden sharing targets, including assessment of sector policies, carbon sinks, and other (economic) instruments. Assistance to Member States, Presidencies and Commission in the UNFCCC negotiations on greenhouse gas monitoring, accounting and reporting. Support to the EU Emission Trading Directive, on guidelines for monitoring, reporting and emission analysis.

2.2 Impacts, adaptation and scenarios

Baseline scenario study linking the long-term climate change convention objective with medium term (2030) societal and policy scenarios. The study will include consequences for air quality and human exposure to pollutants. Improvement of climate change impact indicators. Exploration of possibilities for specific spatial assessments on the impacts of climate change and possible adaptation measures.

Performance indicators:

- successful launch of European pollution emission register (23-02-2004)

- delivery of EU greenhouse gas emission inventory (April 2004)

- issue report on distance to Kyoto targets (end 2004).

3. Nature and biodiversity (216w, 1850kEuro)

3.1 Biodiversity

Preparation for major reporting on the progress towards the 2010 target of halting the loss of biodiversity. Execution of building block studies on high nature value agricultural areas, agri-environmental schemes, fragmentation due to transport infrastructure, biodiversity implementation indicators.  Preparation of the assessments of forest condition under Forest Focus.  Through these activities support implementation and review of the current EC Biodiversity strategy and its action plans. Data handling and evaluation during the process of national designation of areas under the Birds and Habitat Directives (Natura2000) and support to the 25th anniversary of the Birds Directive.

3.2 Spatial assessments

Build capacities within the EEA. Finalise Corine land cover 2000 and produce first assessments of the datasets. Specific spatial assessment of coastal regions to support the interim evaluation of Integrated Coastal Zone Management and of soil contamination to support the Soil thematic strategy.

Building on the 2003 report, develop further short assessments on causes and impacts of natural and technological hazards and explore possibilities for further support in this policy area.

Performance indicators:

- clear plan for 2010 biodiversity progress reporting

- data support for Natura 2000 process for EU15 countries completed and Natura 2000 maps available on the web

- update on impacts of hazards.

4. Environment and health and the quality of life (198w,1850kEuro)

4.1 Environment and human health

Contribute to the development of the cause-effect framework of environment and health and the evaluation of related scientific evidence in support of the EU Environment and Health Action Plan. Exposure assessments (air, drinking water). Contribute to the development of a shared environment and health information platform, in cooperation with World Health Organisation (WHO), including general and children-specific environment and health indicators. Pilot studies on the practical application of the precautionary principle to environment and health issues. Contribute to the Budapest conference of Environment and Health Ministers in June 2004.

4.2 Chemicals

Develop a framework for the monitoring of exposure to chemicals and their impacts on environment and human health, including the improved detection of early warnings and monitoring the effectiveness of measures aimed at reducing exposures and impacts.

4.3 Water quality and Water Framework Directive assessments, including coastal and marine waters

Continued indicator production for assessing progress towards achieving good ecological status of water bodies. Establish the basis for biological priority dataflows. Assessments of agriculture-water relations and nutrient flows as stepping stone towards spatial assessments of ecosystem health including marine eutrophication. Other assessments will be considered on hazardous substances, oil pollution and fishing impact. Prepare with partners joint reports on the Mediterranean and Black Sea. Develop Eurowaternet and Waterbase further in relation to the concept of a shared and accessible Community data and information management system in support of the Water Framework Directive and the Marine thematic strategy.

4.4 Air quality assessments

Production of the regular indicator-based assessment of the effectiveness of national and EU policies in achieving targets for air quality, acidification and eutrophication, heavy metals and persistent organic pollutants and stratospheric ozone. Assessments will include projections to 2010 and exposure indicators. Scenario study on potential air quality targets for 2020.

4.5 Urban areas and noise

Explore options for reporting on the state of the urban environment and ensuring access to data on urban environment to provide better information to the public and to guide and monitor the progress of the Urban thematic strategy. Exploration of the use of noise maps and noise information.

Performance indicators:

- proposal to the Budapest Conference in June 2004 on a common environment and health information system

- Waterbase fully accessible on the web and regular production of water indicators

- delivery of distance-to-target air quality and air emission report (October 2004)

- delivery of summer ozone report (October 2004).

5. Sustainable use and management of natural resources and waste

(72w, 700kEuro)

5.1 Waste and material flow assessments

Develop a methodology to identify resource streams of main concern. Assessment of environmental pressures from different ways of waste treatment and disposal. Produce an environmental outlook for selected waste streams using a macro-economic model linking economic activity with use of resources and generation of waste. Assessment of effects of the implementation of the packaging waste directive.

5.2 Information on best practice

Before embarking on a new, potentially large area of work, define in which areas and in what form EEA can most usefully contribute to dissemination of best practice information and success stories.

Performance indicators:

- methodology for linking material flows with waste and other impacts

- environmental outlook for selected waste streams.

6. International issues and EU in the wider world(72w,200kEuro)

6.1 International & regional organisations cooperation

Memoranda of Understanding with UN bodies, especially UNEP, will be reviewed to take stock of the partnership implemented so far. First preparation activities for contributions to UNEP’s GEO-4. Inputs to GEO-Annual Statement 2004. Workplan for a joint message on the millennium goals. Focussed work with UNEP’s Mediterranean Action Plan on 2004 report on Environment & Development and updated report on the state of the environment of the Mediterranean Sea. Improving information basis (EU-MEDSTAT phase II and UNEP/MAP indicator-based system). Support to EU/MEDA-SMAP annual priority setting: contribution to the Commission study on impact assessment of the free-trade area.

Evaluation of the Kiev report process. Subject to separate funding, further support to EECCA strategy countries with the main objectives of building monitoring capacities and of ensuring participation in the fourth assessment report preparation.

Support streamlining of international reporting with countries and establishment of agreements and partnerships with international organisation to re-organise data flows through the shared information system concept.

6.2. Connect to more regions and countries in the world - Bilateral cooperation

Develop and implement joint activities with USEPA to promote the exchange of information and know-how to improve information management, monitoring and assessment of the environment. Continuous information sharing using the web. Draft and publish joint announcements. Reportnet exchange on IT solutions and maintaining the ecoinformatics website. Second methodological workshop on indicators. Joint meetings with WHO on children environment and health indicators.

Cooperation with other non-European countries. Review EU environment policy relevant to EEA mandate towards main non-member countries and country groups including in particular: China, India and south American and African countries. Establish contacts with environmental agencies in these countries and regular, automatic exchange of information.

Bilateral cooperation with non-EU countries (in progress for Monaco and Switzerland) through improves technical and scientific cooperation between the countries and the EEA. Facilitate information exchange bringing in specific countries’ expertise into the relevant EEA working areas. Improve countries’ knowledge of EEA work and activities at the European level.

6.3 Developing partnerships and links in a wider society

Increase cooperation with wider society (other stakeholders) in the collation, design, development and use of appropriate information such as that being adopted in the development of the 6EAP thematic strategies. Run a series of workshops with a broad number of stakeholders to support an EEA report on Europe’s environment and the global dimension. Develop new indicators on international issues.

### 7. Underpinning environmental policy making (576w, 2400 kEuro)

7.1 Sectoral integration

For transport the activities will focus on maintaining the TERM indicators, with the publication of a summary in autumn. Specific attention will be given to aviation, and the indicators on the implementation of policies for transport-environment integration. For energy the main output will be the energy efficiency success stories report. Scenario results will be included in the energy-environment indicators. Two agri-environment indicator-based reports will be produced at the end of 2004 under the IRENA operation. The other sectors will be screened to identify projects and activities with a high value added.

7.2 Enlargement

EEA will produce a short environmental assessment to coincide with the formal accession of 10 new countries to the European Union, under the auspices of an advisory group of experts from these and other countries. The advisory group will also steer EEA contributions towards the mid-term review of the 6th EAP scheduled for 2006.

7.3 Policy analysis

Two pilot studies will be completed on evaluation of the effectiveness of policies for wastewater treatment and packaging waste.  Depending on the outcome a further pilot study on water pricing will be considered.

Work will continue on framing and piloting EEA activities on policy implementation based on the outcome of the meeting of national Environment Protection Agencies in November 2003.

Work will also continue to improve the OECD/EEA database on economic instruments. EEA will complete an assessment of economic instruments and their application in countries as a contribution to the Commission review process.  Ongoing work on transport externalities will be reviewed and further activities considered for the energy and agriculture sectors.

7.4 Regular cross-cutting assessments

Eight draft sub-reports will be completed as contributions to the 2005 SOER report, covering, sustainable household consumption, biodiversity, sustainable use of resources, policy integration, climate change, Europe’s global environment impacts, environment and health, and scenarios/outlooks.

A short environment Signals report will be published (~25 pages) that tracks progress with EU policies and benchmarks countries environmental performance. Three to four snapshot assessments (~5 pages) will be produced that address issues relevant to ongoing policy processes and different clients’ needs.

7.5 Putting environmental assessments in the context of sustainable development

Support will be given to the assessment and reporting on progress of the EU sustainable development strategy (including its external dimension) and other international and national processes by developing and testing guidelines for environmental assessment and reporting in the context of sustainable development (GEAR-SD) with focus studies on global responsibility and the social interface. A feasibility study will be performed to improve information on sustainable reference values (SRVs). Approaches will also be developed to analyse and disseminate information on sustainable development good practice.

7.6 Emerging issues and research agendas

A few emerging issues, that are arising from scientific research, monitoring, public concerns and from policy analyses, will be identified and selected for analysis and outreach activities. Focus in 2004 will be given to developing further the idea of long term environment and health monitoring, understanding better how to move from information to action (“Bridging-the-Gap” conference Dublin, April 2004), the application of the precautionary principle with case studies on for example nanotechnologies (Stockholm, European Science Forum, September 2004 in cooperation with the European Science Foundation), and the treatment of uncertainty.

7.7 Scenarios and prospective studies

The EEA will develop prospective studies for the State and Outlook Environment Report 2005 and will initiate the sketching of longer term plausible comprehensive European environment scenarios to be used for reference in future EEA work. Preliminary results from a scenario exercise (i.e. PRELUDE) that assesses land use changes in Europe by combining qualitative and quantitative information will be ready for integration in the State and Outlook Environment Report 2005. Scoping studies and feasibility assessments will be undertaken focussing on oil transport and environmental hazards scenarios and on another issue to be determined. Substantial contributions to the Millennium Assessment scenario exercise will continue.

7.8 Tool Box for assessments and methodologies

A methodological guide and framework will be developed for undertaking policy effectiveness evaluations. Work will begin to frame possible EEA activities and contributions on sustainability impact assessment focusing on best practice methodologies. Guidelines will be drafted on terminology and approaches to handling uncertainty and the practical application of precautionary principle. Frameworks and typologies for assessments and indicators will be further elaborated. In order to help improve the role of the public in policy making, the use of stakeholder participation, public attitude surveys and aggregated indicators will be investigated.

5. Administration and Corporate Affairs

The four main management objectives for 2004 are:

- to have a first, full and successful run through the newly defined career development cycle; to have the development path for all staff clear and provide needed coaching and training

- to have a Balanced Scorecard system up and running and monitor the indicators defined in the management plan

- have the management capacities extended through a middle layer of group leaders - and to have it integrated in the line management

- have a management plan system in place and run activity- based management and costing at project level.

# Human resources 2004

|  | Est. table 2003 | Est. table 2004 maximum | Est. table implementation foreseen for 2004 | Contract agents 2004 (indicative) | National Experts (indicative) |
| --- | --- | --- | --- | --- | --- |
| A2 – A3 | 4 | 5 | 4 |  |  |
| A4 – A5 | 18 | 21 | 17 |  |  |
| A6 – A7 | 26 | 25 | 30 | 5 |  |
| B | 33 | 34 | 34 | 5 |  |
| C | 25 | 26 | 22 |  |  |
| D | 4 | 4 | 4 |  |  |
| Total | 111 | 115 | 111 | 10 | 14 |

# Financial resources 2004

| Budget | 2003 | 2004 |
| --- | --- | --- |
| title 1 (staffing) | 11723 | 13460 |
| staffing Off. + temp. agents | 8730 | 10540 |
| auxilliary | 850 | 420 |
| other lines |  | 2500 |
| title 2 (building) | 2909 | 3040 |
| title 3 (operational) | 12889 | 13330 |
| chapter 3.1 |  |  |
| contract agents |  | pm |
| meetings | 729 | 750 |
| translation | 720 | 700 |
| IT core | 900 | 900 |
| Communications | 700 | 980 |
| Electronic communications services | 670 | 700 |
| Topic Centre ACC |  | pm |
| Topic Centre WTR |  | pm |
| Topci Centre NPB |  | pm |
| Topic Centre TE |  | pm |
| Topic Centre WMF |  | pm |
| chapter 3.2 |  |  |
| SA1 Information systems | 1310 | 1200 |
| SA2 Climate change | 1150 | 1100 |
| SA3 Nature & biodiversity | 2260 | 1850 |
| SA4 Env, health and quality of life | 1840 | 1850 |
| SA5 Natural resources & waste | 730 | 700 |
| SA6 International issues | 0 | 200 |
| SA7 Underpinning Env. policy making | 1880 | 2400 |
| total budget | 27521 | 29830 |

# 6. Communications highlights

The main management communication objectives for 2004 are:

- to have in place a communications strategy;

- to have specific communications activities running throughout the Agency;

- to provide the needed coaching and training for staff to help them become more effective communicators; and

- to have a modest programme of new communications initiatives designed to increase the visibility of the Agency and develop our role to communicate effectively in support of environmental policy making.

Major publications

In 2004 a series of new product-lines will be introduced, e.g. EEA briefings, aimed at providing more focused information to key clients and the public. Other major publications – mainly issue and assessment reports - in 2004 will be:

Signals 2004

Signals snapshots

Progress towards the Kyoto Protocol targets

Annual greenhouse gas inventory report

Greenhouse gas trends and projections

Europe’s Biodiversity

Impact of biofuel on habitats and biodiversity

Joint EEA-UNEP message on agriculture and biodiversity

State of Europe's soils

Summer ozone in 2004

Progress towards air quality and emission targets

Annual air pollutant emission inventory

Towards better environment and health assessments and indicators

Effectiveness analysis of waste packaging directive

Report on environmental-economic issues relating to EEA activities

Energy efficiency success stories

Transport and environment reporting mechanism (TERM)

Fisheries and aquaculture

Contribution to 25th anniversary of EU Birds Directive

Core set of indicators

Electronic communications services

All EEA publications are prepared for EEA products for cross-media publishing and made accessible on the EEA web site.  The site is also continuously being improved and increasingly supporting the multilingual user community. A user survey and usability study will be conducted in 2004 in order to guide the further development of the site.

The list below includes the main new items that will be launched on the web site in 2004 in addition to the reports listed above and the Agency’s more technical reports.

European Pollution Emission Register

OECD/EEA database for economic instruments and voluntary approaches

New section on sustainable development and web application for sustainable development indicators

Web application for presentation of agriculture and environment indicators

New section dedicated to scenarios

New section dedicated to products targeted to a younger audience

Pilot portal to local environmental information (in co-operation with relevant national initiatives)

Information centre electronic services

Service for customers to personalise web update notifications

Major events

The Agency will be organizing two major events in 2004:

EPER Launch together with DG ENV, Copenhagen

10th Anniversary week - festival of environmental meetings, Copenhagen

and supporting two major conferences being organized by others:

Bridging the Gap Conference, Dublin

Conference of Environment and Health ministers, Budapest

Activities presented elsewhere in this plan will contribute directly to the objectives introduced here.